## Sheet1
# | Name | Type | PIC | Start date | End date | Description | kick-off 1 | completion 1 | Non-negotiable | Complexity | Quick-win | Impact | Prioritas
6.1 | Organization Development | P |  | 2014-09-01 | 2016-05-01
6.1.A | Organisation Development for Wholesale | I | Tommy L., Dody H. (HCP) | 2014-09-01 | 2015-03-14 | New organisation rollout for wholesale based on new corporate plan 2015-2020 cover SO, JD, talent panel, and change management |  |  |  | High |  | High | 1
6.1.B | Organisation Development for Retail/ Distribution | I | Tommy L., Dody H. (HCP) | 2014-09-01 | 2015-03-31 | New organisation rollout for retail based on new corporate plan 2015-2020 cover SO, JD, talent panel, and change management |  |  |  | High |  | High | 1
6.1.C | Organisation Development for All Other Job Family | I | Tommy L., Dody H. (HCP) | 1-Oct-14 | 2015-04-30 | New organisation rollout for bankwide based on new corporate plan 2015-2020 cover SO, JD, talent panel, and change management |  |  |  | Medium |  | High | 1
6.1.D | Review Grade Structure & Alignment with Subsidiaries | I | Tommy Lianto (HCP) | 1-May-15 | 30-Dec-15 | Review internal grade structure based on new organisation structure and harmonise grade structure to align with all subsidiaries |  |  |  | High |  | High | 1
6.1.E | Career Paths Development for all job family | I | Tommy Lianto (HCP) | 2015-02-01 | 1-May-16 | Develop career paths for jobs in wholesale, retail and supporting units |  |  |  | Medium |  | High | 2
6.1.F | Strategic Workforce Planning Enablement & Roll Out | I | Anita W., Tommy L. (HCP) | 2015-03-01 | 30-Oct-15 | Define strategic workforce planning approach and methodology. Prepare relevant data to be accessible for workforce planning tools. Develop Strategic Workforce Planning tool & rollout. |  |  |  | High |  | High | 2
6.1.F | Redefine and elevate HCBP role | I | Tommy Lianto (HCP) | 2014-09-22 | 2015-01-31 | Define new Job Descriptions, new KPIs for HCBP. Elevate HC business partner role in relationship and integrated with Human Capital management system in bankwide. |  |  |  | High |  | Medium | 3
6.2 | Capability Development | P |  | 2014-01-09 | 2015-05-30
6.2.A | Capability Development for Wholesale | I | Lila Noya (MU) | 2014-01-09 | 2015-03-31 | Define Capability Advancement Plan for jobs in Wholesale, upgrade the RM competency and develop learning curriculum for Wholesale Segment | 1.3.B |  |  | high |  | High | 1
6.2.B | Capability Development for Retail/Distribution | I | Lila Noya (MU) | 2014-01-10 | 2015-04-30 | Define Capability Advancement Plan for jobs in Retail & Distribution and develop learning curriculum for Retail Segment | 3.1.A,3.3.B |  |  | high |  | High | 1
6.2.C | Capability Development for All Other Job Family | I | Lila Noya (MU) | 2014-01-09 | 2015-03-31 | Define Capability Advancement Plan for jobs in Bankwide and develop learning curriculum |  |  |  | high |  | High | 1
6.2.C | Curriculum Development ODP Program | I | Lila Noya (MU) | 2014-09-19 | 2015-01-31 | Develop Curriculum Development ODP Program which includes improvement in classroom & on the job training |  |  |  | medium |  | High | 2
6.2.D | HIPO Development Program | I | Lila Noya (MU) | 19-Oct-14 | 30-May-15 | Develop leadership advancement plan for HIPO development. |  |  |  | medium |  | High | 2
6.2.E | Leverage Mandiri University for Subsidiaries | I | Lila Noya (MU) | 19-Oct-14 | 30-May-15 | Pilot project to leverage Mandiri University to build workforce capability for 1 subsidiary – with rollout to others gradually |  |  |  | medium |  | Medium | 2
6.3 | Recruiting | P |  | 2014-11-01 | 2015-06-30
6.3.A | Recruiting Strategy for Fresh Graduates Hiring | I | Mustaslimah | 2014-11-01 | 31-May-15 | Review Current Recruitment selection criteria, hiring process, and recruitment SLA for all fresh graduate sourcing |  |  |  | High |  | High | 1
6.3.B | Recruiting Strategy & Execution - Wholesale | I | Mustaslimah | 2014-11-01 | 31-May-15 | Review profiling tools, selection criteria for all sourcing, i.e. External and internal sourcing, hiring process and recruitment SLA for wholesale segment |  |  |  | High |  | High | 1
6.3.C | Recruiting Strategy & Execution - Retail/ Distribution | I | Mustaslimah | 2014-11-01 | 31-May-15 | Review profiling tools, selection criteria for all sourcing, i.e. External and internal sourcing, hiring process and recruitment SLA for retail segment |  |  |  | High |  | High | 1
6.3.D | Recruiting Strategy & Execution – Supporting Roles | I | Mustaslimah | 2014-11-01 | 31-May-15 | Review profiling tools, selection criteria for all sourcing, i.e. External and internal sourcing, hiring process and recruitment SLA for Bankwide supporting roles |  |  |  | Medium |  | High | 1
6.3.E | Streamlining Recruitment Processes | I | Mustaslimah | 2014-11-01 | 2015-06-30 | Streamlining of roles & accountability across HC Strategy, HC Services, HCBP to deliver recruiting outcomes |  |  |  | High |  | High | 1
6.3.F | Internal Job Posting (Internal Group & to Subsidiaries) | I | Mustaslimah | 2014-03-01 | 30-Oct-15 | Enable the talent mobility process for internal recruitment |  |  |  | Medium |  | Medium | 2
6.4 | Talent Management | P |  | 2014-10-01 | 2016-04-30
6.4.A | Develop Talent Accountability Method | I | Dody Hermawan (HCP) | 1-Oct-14 | 2016-04-30 | Recaliberate the talent classification & successor identification process and talent classification quotas; Formulate policies and enable talent mobility program. |  |  |  | High |  | High | 1
6.5 | Reward & Performance Management | I |  | 2014-09-15 | 2015-10-30
6.5.A | Development compensation & benefit scheme by jobs family | I | Eka Fitria (HCP) | 2014-11-01 | 30-Oct-15 | Design improvement for compensation & benefit to drive a strong pay for performance culture and linkage to Mandiri's new corplan strategy. |  |  |  | High |  | High | 1
6.5.B | Bankwide Benefit Review | I | Eka Fitria (HCP) | 2014-09-15 | 30-Oct-15 | Design improvement for current bankwide benefits items |  |  |  | High |  | High | 2
6.5.C | Improvement on Individual KPI Setting | I | Eka Fitria (HCP) | 2014-09-15 | 30-Oct-15 | Review KPI setting process and develop revised KPI setting approach |  |  |  | High |  | High | 3
6.6 | HC Service Delivery & Technology | P |  | 2014-10-01 | 2017-06-01
6.6.A | HC Process Alignment & System Integration in Bank Mandiri | I | Anita Widjaja (HCP) | 1-Oct-14 | 2016-06-30 | Perform system improvement and process SLA for current HC technology. Improve integration process and data flows among the systems. |  |  |  | High |  | High | 1
6.6.B | HC Services Process Alignment & Improvement (SLA Driven processes + Incorporate Field HC into HC Services + HC & Employee Portal) | I | Wawan P (HCP) | 1-Oct-14 | 2015-03-31 | Improve SLA-driven HC services support for all transactional HC functions - Payroll, employee data management, onboarding, recruiting |  |  |  | High |  | High | 1
6.6.C | Group-wide vendor management | I | Wawan P (HCP) | 2014-11-01 | 2016-06-30 | Create centralized, groupwide vendor management function, |  |  |  | High |  | Medium | 2
6.6.D | Group wide harmonization of process and technology | I | Anita Widjaja (HCP) | 2015-11-01 | 2016-06-30 | Assess group-wide HC processes and align with Mandiri policy and processes |  |  |  | High |  | High | 2
6.6.E | HC Shared Services Development | I | Anita Widjaja (HCP) | 2016-06-01 | 2017-06-01 | Analyze shared service for Mandiri and its subsidiaries |  |  |  | High |  | High | 2
6.7 | Employee Value Proposition | P |  | 2014-10-01 | 2016-12-31
6.7.A | Internal & External validation of understanding and attractiveness of the EVP | I | Ni Luh (CSP) | 1-Oct-14 | 2015-01-31 | Internal & External validation of understanding and attractiveness of the EVP. Develop communication strategy and branding quick win through career site. |  |  |  | High |  | High | 1
6.7.B | External deployment of the EVP | I | Ni Luh (CSP) | 2015-01-01 | 30-Dec-15 | Develop external activation campaign materials (videos, posters, brochures): a) Career website and internal job posting site; b) Career fairs; c) University outreach; d)Social media hiring channels |  |  |  | High |  | High | 1
6.7.C | Internal deployment of the EVP (incl. Enabling change agent to deliver EVP message) | I | Ni Luh (CSP) | 2015-01-05 | 30-Dec-15 | Develop internal activation campaign on EVP covers capability development for managers and change agents in terms of delivering the EVP and enabling change |  |  |  | High |  | High | 2
6.7.D | Enabling change management in HC | I | Nenden N., Lila Noya (HCP, MU) | 2015-07-01 | 31-Dec-16 | Institutionalize a robust change management methodology across all HC programs, which is also supported by the business. Also to integrate communication with subsidiaries |  |  |  | High |  | High | 2
Formulas:
Start date = MIN([Start date, row below]:E9)