## Sheet1
# | Name | Type | PIC | Start date | End date | Description | kick-off 1 | completion 1 | status | Non-negotiable | Complexity | Quick-win | Impact | Prioritas
3.1 | Develop leading micro credit risk management system and culture | P |  | 2015-01-01 | 2017-10-31 | -Implementing/cascading disciplined and active RTTA portfolio management practices in clusters and branches/units -Continuous updating of early detection system & development of early warning system -Improved Micro credit scoring model and development process |  |  |  | Critical for RTB | 2 - low |  | 3 - High | 1
3.1.A | Improve portfolio management by micro leadership in each level | I | Ashraf Farahnaz (RTR) | 2017-01-01 | 2017-10-31 | Implement RTTA process that has been effective in MBDCs level to be replicated for clusters and branch level | 5.6.B |  |  | Critical for RTB | 2 - low | Quick-win | 3 - High | 1
3.1.B | Evolve early detection system and follow up mechanism / Add early warning system | I | Ashraf Farahnaz (RTR)
3.1.C | Longer term investment in credit scoring methodology and dataset | I | Ashraf Farahnaz (RTR & MBG shared scoring system) | 2015-01-01 | 2015-12-31 | -Establish a reliable micro credit scoring methodology and spend resources and time to obtain the required data for an extended period of time |  |  |  | Foundational | 4 - high | N/A | 3 - High | 1
3.2 | Making Mandiri a highly reputed Micro bank | P |  | 2014-07-01 | 2014-12-31 | -Combination of CSR initiatives, academic / industry collaborations and internal policy guidelines that will raise the level of awareness on merits of Mandiri’s Micro business |  |  |  | N/A | 2 - low |  | 3 - High | 1
3.2.A | Corporate Social Responsibility movement on Micro Entrepreneurship | I | Sigit Aryo Tejo (MBG) | 2014-07-01 | 2014-12-31 | -Develop active involvement from employees in micro distribution for better ownership and improving closeness to communities -Develop, standardized ready to use tools curriculum and guidance provided by head office |  |  |  | N/A | 2 - low | N/A | 3 - High | 1
3.2.B | Annual Micro Mandiri Awards and International Micro Seminars | I | Sigit Aryo Tejo (MBG) | 2014-07-01 | 2014-12-31 | Finalized concept design for: -Mandiri Micro awards: given annually to local heroes, BPR, branches and employees with extraordinary contribution in Micro -Mandiri Micro Innovation awards: for basic but effective technology that is useful for development of micro enterprises |  |  |  | N/A | 2 - low | N/A | 1 - Low | 2
3.2.C | Quarterly Mandiri Micro Journal publication | I | Sigit Aryo Tejo (MBG) | 2014-07-01 | 2014-12-31 | -Work with university/think tank to aggregate academic paper, review and publish journals -Publish Journals regularly for academic and public consumption and distribute |  |  |  | N/A | 2 - low | N/A | 1 - Low | 2
3.3 | Fast track Branch led expansion in Semi Urban locations | P |  | 2014-07-01 | 2015-12-31 | -Branch led coverage in Semi Urban locations will be the key priority -Structured and methodical periodical selection of new market location -Talent model, sourcing and development as well regionalization of support |  |  |  | Critical for RTB | 3 - medium |  | 3 - High | 1
3.3.A | Branch expansion base on micro corplan 2020 to achieve total 4300 networks in 2020 | I | Sigit Aryo Tejo (MBG) | 2014-09-01 | 2014-10-31 | -Establish the capability and database in Micro HO & Districts to conduct desk research for the next best new market in semi annual basis -Implement a disciplined three step process and timeline in new market selection -Standardize criteria for organic growth in existing market |  |  |  | Critical for RTB | 3 - medium | N/A | 3 - High | 1
3.3.B | Develop staff talent sourcing, placement and development to meet resource requirement in new branches | I | Febrijanti (HCBP Micro & BB) | 2014-07-01 | 2015-07-31 | -Scale up recruitment capacity of micro staffs especially MKS and support staffs -Scale up training capacity of micro staffs in the region |  | 6.3.B |  | N/A | 3 - medium | N/A | 3 - High | 2
3.3.C | Remodeling branch Staffing requirement to address leadership talent gap in network expansion | I | Febrijanti (HCBP Micro & BB) | 2014-07-01 | 4/31/2015 | -Remodel current branch resourcing requirement and policy to allow MMM to lead micro lean branch (including alternative of Teller coordinator to accompany MMM) -Set new model as the new policy of new staffing model for Lean branch |  | 6.2.A,6.5.B |  | N/A | 4 - high | N/A | 2 - Medium | 1
3.3.D | Establish new sourcing initiatives for MMM | I | Febrijanti (HCBP Micro & BB) | 2014-09-01 | 2015-03-31 | -Determine and agree on the new potential source of MMM (i.e. from P3K, local fresh grad, CSO etc.) -Establish M3 Leadership Boot Camp & Assessment to allow P3K to becomes M3 without going through the traditional and more academic SDP PPMM -Establish ODP regional to acquire local talent for local placement |  |  |  | N/A | 3 - medium | N/A | 2 - Medium | 1
3.3.E | Decentralize elements of HO decision making and develop Micro HC competence in MBDCs | I | Febrijanti (HCBP Micro & BB) | 2014-07-01 | 2014-10-31 | -Regionalization of branch development, recruitment, staff training and operational support to MBDCs which currently conducted centrally by Micro HQ or Regional office (Kanwil) -Additional headcount will be needed in MBDCs as the number of supported staffs and networks grow |  |  |  | Critical for RTB | 2 - low | N/A | 2 - Medium | 2
3.3.F | Realign operational process post lean branch embedded to Mandiri distribution organization | I | Rusdan Usman (DBS) | 2015-03-01 | 2015-12-31 | -Assessment of current process on Market selection, front office operation, hard cash management, IT systems, and operation quality control -Identify and implement improvements |  |  |  | Critical for RTB | 3 - medium | N/A | 3 - High | 2
3.4 | Development and roll out of “Lean branch” format | P |  |  |  | -Micro branch format will need to be upgraded to “Lean branch” to improve branch economic model; current micro branch layout sufficient to support lean branch |  |  |  | N/A | 3 - medium |  | 2 - Medium | 2
3.4.A | Develop the prototype of “Lean branch” and required sales / servicing capabilities, pilot & roll out | I | Rusdan Usman (DBS) & Corporate Transfomations |  |  | -Determine products and services to be sold and referred in Lean Branch (i.e. what non-micro product to be offered through referral, savings product and basic services to be offered) -Define lean branch staffing model -System, product and marketing collateral development of selected products '-Pilot “Lean branch” in different geographies and different segments -Pilot in full lean branch staffed branch and in existing micro branch staffing '-Up-skill existing CS product knowledge and sales confidence -Determine the existing lean branches that are prioritized for additional staffing -Staged fulfillment of staffing required |  |  |  | N/A | 3 - medium | N/A | 2 - Medium | 2
3.4.B | Align performance management structure to optimize lean branch | I | Sigit Aryo Tejo (MBG) |  |  | -Significantly shifting micro CS service oriented KPI into a more sales oriented Sales generalist KPI -Develop Activity and sales monitoring system for new type CS -Align KPI of other staffs in micro distribution for Savings and cross sell of non-micro products |  |  |  | N/A | 3 - medium | N/A | 2 - Medium | 2
3.5 | Development of scalable Rural Micro franchise expansion model | P |  | 2014-07-01 | 2015-07-31 | -Combination of extensive partnership pilots, branch anchored agents and cluster based footprint development expansion in Rural locations |  |  |  | Critical for RTB | 3 - medium |  | 3 - High | 1
3.5.A | Pilot multiple Rural partnership model across multiple partners | I | Sigit Aryo Tejo (MBG) | 2014-07-01 | 2015-07-31 | Pilot four partnership models for savings and loan referrals with a variety of potential partners |  | 6.2.A,6.5.B |  | Critical for RTB | 3 - medium | Pilot | 3 - High | 1
3.5.B | Pilot next phase of agent based banking anchored around “Lean branches” | I | Sumedi (MBG) | 2014-07-01 | 2015-07-31 | -Test effectiveness of agents recruitment and on-boarding training -Test attractiveness of incentive scheme for agents -Test the level of support needed from Lean branch to maintain agents -Test fraud prevention and corrective mechanism |  | 6.2.A,6.5.B |  | Critical for RTB | 3 - medium | Pilot | 3 - High | 1
3.5.C | Identify successful pilots and fast track to roll out solutions | I | Sumedi (MBG) | 2015-07-01 | 2015-10-31 | -Assess the most effective partnership / agent-based model -Develop pipeline of potential partners based on model -Roll out agent recruitments |  | 6.2.A,6.3.B,6.5.B |  | N/A | 3 - medium | N/A | 3 - High | 1
3.5.D | Develop selected Rural markets via cluster based network expansion approach | I | Sigit Aryo Tejo (MBG) | 2014-07-01 | 2015-07-31 | -Develop policy of selecting new branches through cluster approach -Roll out clusterized branch development around “core” branch |  | 6.2.A,6.5.B |  | Critical for RTB | 2 - low | Pilot | 2 - Medium | 1
3.6 | Enhancing operational excellence in Micro business | P |  | 2014-07-01 | 2014-12-31 | -Test and roll out a number of operational improvement initiatives across Micro operations – Loan factory document validation / MKS mobile app |  |  |  | N/A | 4 - high |  | 2 - Medium | 2
3.6.A | 3-in-1 Digital application for MKS | I | Hery Sofiaji (MBG) |  |  | Define business requirement, develop, test and roll out MKS mobile app that include -Sales and pipeline tracking application -Loan status update and tracker -Collection tracker and scheduling application |  |  |  | N/A | 4 - high | N/A | 2 - Medium | 2
3.6.B | Establish integrated portfolio view | I | Hery Sofiaji (MBG) | 2014-08-01 | 2014-10-31 | Develop platform to enable integrated portfolio view that can be readily accessed, that include: -Network profiles (location, neighborhood, competition etc.) -Portfolio performance and quality -Tracking of historical ownership of accounts |  |  |  | N/A | 5 - very high | N/A | 2 - Medium | 2
3.6.C | “Loan factory” based document verification process | I | Hery Sofiaji (MBG) | 2014-07-01 | 2014-12-31 | -Design part of verification requirement and process that can be centralized -Pilot centralized verification process and continually fine tuning the policy and process -Define geographies of Micro network that will be centralized (versus geographies that will stay decentralized) |  |  |  | N/A | 3 - medium | Pilot | 2 - Medium | 2
3.6.D | Streamlining payroll offering | I | Hery Sofiaji (MBG) | 2014-07-01 | 2014-10-31 | -Improve policy for sourcing for companies that are eligible for payroll -Staged roll out of areas where KSM is centralised and decentralised |  |  |  | N/A | 2 - low | N/A | 1 - Low | 2
3.7 | Developing next generation installment savings plan proposition | P |  | 2014-07-01 | 2015-10-31 | -Product design, packaging and offer marketing that encourages Micro business owners / Mass market individuals to save regularly |  |  |  | N/A | 3 - medium |  | 2 - Medium | 2
3.7.A | Design and develop product platform, product packages & bundled, pilot & roll out in stages | I | Hery Sofiaji (MBG) | 2014-07-01 | 2015-10-31 | -Design installment savings plan features, value proposition and mechanics of its linkage with micro loans -Enhance system to facilitates smooth and simple operations of product 'Establish a number of product packages for different customers in micro network using one product platform '-Pilot implementation of the product platform -Train sales for product knowledge and change in mindset -Align performance management to favor sales and maintenance of installment savings plan |  |  |  | N/A | 3 - medium | N/A | 2 - Medium | 2
3.7.B | Develop marketing and communication strategies around “product bundles” | I | Hery Sofiaji (MBG) | 2015-04-01 | 2015-07-31 | -Develop marketing and communication strategy -Establish simple and suitable sales tools for use in branch |  |  |  | N/A | 3 - medium | N/A | 2 - Medium | 2
Formulas:
Start date = MIN([Start date, row below]:E5)
End date = MAX([End date, row below]:F5)
End date = MIN([End date, row below]:F24)