## Sheet1
# | Name | Type | PIC | Start date | End date | Description | kick-off 1 | completion 1 | Status | Non-negotiable | Complexity | Quick-win | Impact | Prioritas
1.1 | Enhance service excellence | P |  |  |  | Establish client tiering for wholesale customers and value chain
1.1.A | Align and map (existing) client tiering | I | Lead :Gaby Valeria Team:Hermawan Soebagio | 2014-11-01 | 2015-06-30 | Single client tiering model across wholesale & map clients (anchors) |  |  | In Progress | Foundational | 3 - medium | Quick-win | 3 - high | 1
1.1.B | Define service points and formalise and unify SLAs | I | Lead :Gaby Valeria Team: Antonius Kunta Widyatmaka | 2015-07-01 | 2015-12-31 | Etablish service level by tiers & formalize SLAs (anchors) |  | 1.1.A | In Progress | N/A | 3 - medium | Pilot | 3 - high | 1
1.1.C | Enhance Service Level | I | Lead :Gaby Valeria, Team: Basu Vitri Manugrahani, Antonius Kunta Widyatmaka, Nita | 2016-01-01 | 2016-10-31 | Enhance service capabilities accross channels |  |  | In Progress |  | 3 - medium |  | 2 - Medium | 2
1.1.D | Establish credit analyst team | I | Lead: Kepas A.A.Manurung, Tiwul Widyastuti, Titiek Setyowati, Sucipto Prayitno Team: Farid Ma'ruf, Mindha Erdismina, Erwin Khristianto | 2014-06-01 | 2015-10-15 | Create dedicated credit analyst team to free up RM time (pilot) |  | 7.1.A,7.1.B | In Progress |  | 3 - medium |  | 3 - High | 1
1.1.E | Implement full CST service model | I | Lead :Gaby Valeria Team:Hermawan Soebagio | 2014-12-01 | 2015-06-30 | Migrate clients to full CST model with lead RM |  |  | In Progress | Foundational | 3 - medium | Pilot | 3 - high | 1
1.1.F | Design and roll out integrated customer portal | I | Lead: Riza Zulkifli Team: Gaby Valeria, Billy Hotbah M. Tuah Damanik, Andy Puguh Nugroho, Antonius Kunta Widyatmaka | 2015-03-30 | 2017-08-31 | Develop integrated customer portal to improve product delivery |  | 5.1.T | Not Started Yet | N/A | 4 - high | Pilot | 2 - Medium | 3
1.2 | Develop sector solutions | P |  |  |  | Developing and piloting proposition for priority sectors
1.2.A | Wholesale Portfolio Segmentation | I | Lead: Oliver Wyman | 2014-06-01 | 2015-01-31 | Redefine client segmentation: corporate, commercial, MSME |  |  | Completed |  | 3 - medium |  | 3 - High | 1
1.2.B | Complete healthcare and port pilot and full roll out | I | Healthcare Lead: Arya Suprihadi Team: Andrianto Wahyu Adi, Sunarto Xie, Dyah Eti Irawati Port Lead: Indarto Pamoengkas Team: Andrianto Wahyu Adi,Buyung I Lukman, Sunarto Xie | 2015-01-01 | 2015-12-31 | Continue existing PCM efforts & launch solutions |  | 8.1.H | In Progress | N/A | 4 - high | Pilot | 3 - High | 1
1.2.C | Launch Proposition across other sectors: FMCG-F&B, Plantation, Oil&Gas,Goverment,Telco,Building Materials,Infrastructure | I | Sector Solutions Lead: Rustam S. Sirait Team:Tongki Lentari FMCG-F&B Lead: Yusac L Silalahi Team: M. Iswahyudi Plantation/Agribusiness Lead: Sucipto Prayitno Team: Nurulloh Priyo Sembodo Oil&Gas Lead: Alexandra Wiyoso Team: Faiz Firdausi Government Lead :Indarto Pamoengkas Team: Arya Suprihadi, Deny Edward Yusar Telco Lead: Teddy Danas Team: Dwi Astuti Rahayu Building Materials/Konstruksi Lead: Maqin Norhadi Team: Prihanto Herbowo | 2014-09-01 | 2017-05-31 | Coordinate, detail & launch sector initiatives across priority sectors | 2.2.A,2.2.B |  | In Progress | N/A | 4 - high | Pilot | 3 - high | 1
1.3 | Build out sector expertise | P |  | 2015-02-01 | 2017-03-31 | Build Self branding as an expert in sectors priorities , including ensuring the competence upgrade
1.3.A | Build out sector branding | I | Lead: Tba (Strategic Marcomm) Team: Gaby Valeria, Ilham Farizal, Hermawan Soebagio | 2015-10-01 | 2017-03-31 | Align branding with sector proposition across priority sectors |  |  | Not Started Yet |  | 2 - low | N/A | 2 - Medium | 3
1.3.B | Upgrade RM Competency | I | Lead: Gaby Valeria Team: Anita Widaja, Stefan, Hermawan Soebagio | 2015-03-01 | 2016-02-29 | Upgrade RM skill set according to enhanced RM competency model |  | 1.2 | Not Started Yet | N/A | 2 - low | N/A | 3 - High | 3
1.3.C | Enhance Sector Information Support | I | Lead :Gaby Valeria Team:Hermawan Soebagio | 2015-02-01 | 2015-04-30 | Ensure RM access to internal & external industry knowledge |  |  | Not Started Yet |  | 3 - medium |  | 2 - Medium | 3
1.4 | Enhance product suite | P |  | 2013-10-01 | 2019-03-31 | Develop propositions related products IWTB , ie SCF , MCM , Trade Fin , Structured Fin , Capital Market , including cross - border offering and FI
1.4.A | Upgrade SCM | I | Lead: Andrianto W Adi Team:Trilaksito Singgih | 2013-10-01 | 2015-04-30 | Upgrade SCF platform to meet client functionality needs |  |  | In Progress | N/A | 3 - medium | Pilot | 2 - medium | 2
1.4.B | Upgrade MCM | I | Lead: Andrianto W Adi Team: Prita Sesanti | 2014-08-01 | 2019-03-31 | Upgrade MCM platform to meet target state PCM functionality |  |  | In Progress |  | 3 - medium |  | 2 - Medium | 2
1.4.C | Upgrade Trade Finance | I | Lead: Andrianto W Adi Team: Trilaksito Singgih | 2014-07-01 | 2016-09-30 | Enhance service standards & pricing |  |  | In Progress |  | 3 - medium |  | 2 - Medium | 2
1.4.D | Build out Structured finance | I | Lead: Alexandra Askandar Team: Rony Kuntadi | 2015-03-02 | 2015-09-30 | Build out core project finance offering |  | 6.1.A | Not Started Yet | N/A | 4 - high | Pilot | 2 - medium | 2
1.4.E | Upgrade Capital Markets offering | I | Lead: C.Paul tehusijarana Team: Andreas Muljadi Gunawidjaja | 2015-02-01 | 2016-12-31 | Build out Capital Market and inbound FDI advisory capabilities |  | 6.3.A | In Progress | Foundational | 4 - high | Pilot | 2 - medium | 2
1.4.F | Upgrade Cross border offering | I | Lead: Ferry M. Robani Team: Rahmawati | 2014-12-01 | 2016-06-30 | Close critical gaps in intl product offering; tie with MCM replacement |  | 6.3.A | In Progress | Foundational | 4 - high | N/A | 2 - Medium | 1
1.4.G | Upgrade FICS offering | I | Lead: Ferry M. Robani (IBFI) Team: Agus Kunaepi | 2014-08-01 | 2015-04-30 | Upgrade domestic custody offering & outsourcing capabilities |  |  | In Progress | Foundational | 3 - medium | N/A | 2 - medium | 2
1.5 | Upgrade CRM and MIS tools | P |  | 2015-03-30 | 2017-02-24 | Upgrade key data infrastructure (CRM & MIS)
1.5.A | Improve data management, capture and access | I | Lead: Riza Zulkifli Team: Mahesh Ranade, Billy H Damanik, I Made Wahyu | 2015-03-30 | 2016-05-27 | Ensure data is fit for purpose & captured systematically | 5.2.A |  | Delay | N/A | 4 - high | N/A | 3 - High | 2
1.5.B | Upgrade CRM | I | Lead: Riza Zulkifli Team: Mahesh Ranade, Billy H Damanik, I Made Wahyu | 2015-03-30 | 2017-02-24 | Integrate data sources to create 360 degree customer view |  |  | Not Started Yet |  | 4 - high |  | 3 - High | 2
1.5.C | Upgrade MIS | I | Lead: Riza Zulkifli Team: Mahesh Ranade, Billy H Damanik, I Made Wahyu | 2015-03-30 | 2017-02-24 | Provide single data interface and source of truth across the bank |  |  | Not Started Yet |  | 4 - high |  | 3 - High | 2
1.6 | Develop relationship pricing | P |  | 2016-01-01 | 2019-04-30 | Develop pricing strategy and policy , including pricing intelligence function
1.6.A | Establish pricing strategy, map clients, and formalise pricing policies | I | Lead: Gaby Valeria Team: Antonius Kunta Widyatmaka | 2016-01-01 | 2018-05-31 | High level strategic guidance for pricing decisions & policies |  | 5.5.A | Not Started Yet | Foundational | 4 - high | Pilot | 3 - High | 1
1.6.B | Establish pricing intelligence function | I | Lead: Gaby Valeria Team: Antonius Kunta Widyatmaka | 2016-01-01 | 2017-12-31 | Establish function to collate & analyze market pricing information |  |  | In Progress |  | 3 - medium |  | 2 - Medium | 2
1.6.C | Pricing tool review and upgrade | I | Lead: Gaby Valeria Team: Antonius Kunta Widyatmaka | 2018-02-01 | 2019-04-30 | Ensure pricing tools are understood, user friendly and fit for purpose |  |  | Not Started Yet | N/A | 4 - high | N/A | 3 - high | 1
Formulas:
Start date = MIN([Start date, row below]:E16)
End date = MAX([End date, row below]:F16)